## Dataset
Statement | Question
All testing to date indicates that bismuth growth initiates and progresses only during vacuum-bake out – temperature cycling without vacuum does not exacerbate growth of whiskers | Is there a correlation between the failures exhibited at final test and the number of vacuum-bake
Whisker growth present after first vac-bake cycle, continued growth after second vack-bake cycle | Is there a correlation between the number of vac-bake cycles and the length of the bismuth whiskers? If so, can we identify which units were subjected to the number of vac-bake cycles that could yield whiskers of a length to cause short?
LMC does not have a hard limit for vacuum-bake or vac-bake cycles for production hardware, but rarely do modules perform more than one cycle. ADF is the supplier | The chart states that LMC typically subjects units to only one vac-bake cycle (although there is no limit). Based on the conclusion that additional vacuum-bake cycles lead to increased whisker growth, are there units delivered at more risk due to the number of vac-bake cycles they were subjected to? Can LMC provide a list of serial numbers and the corresponding number of vac-bake cycles they were subjected to? Can ADF do the same?
Final results of Test Scenario 2 ECD – July 18th | request the results of the Test Scenario 2 once available.
Test Scenario 2 used to determine if bismuth whiskers are liberated when exposed to mechanical shock and vibration. Unit selected exhibited significant quantity of bismuth whiskers. No observable liberation or relocation of whiskers | How many units were subjected to the Scenario 2 mechanical response testing? The chart seems to imply only one. What was the condition of the unit(s) tested relative to bismuth whisker length?
125degC soak under vacuum followed by ATP, PIND, Vibe, and ATP. Repeated three (3) times on five units | What was the ATP result (pass/fail) after each cycle of vac-bake?
Four (4) units selected had already gone through 4 vacuum-bake cycles, burn-in, temp, and ATP All units baked with no vacuum and then sealed. All units performed ATP testing | Did the 4 units all pass ATP after the initial 4 vac-bake cycles?
Two units exposed to 33 temp cycles | Did they pass ATP after the two 33 temp cycles?
The two typical flow units completed temp cycle and are staged for burn-in (results not yet verifiable) | When will the post test internal inspection results be available for the two units that underwent the typical process flow?
all 5 units failed at 500 hour read point | the fact that all 5 units failed at the 500 hour read point is concerning. Need to understand the impact of this.
Supplier reliability testing to date strongly indicates whisker growth occurs only under vacuum bake out. The module seal is performed post-vacuum bake out and in an inert gas environment at standard pressure – no additional growth of whiskers expected | Do we believe that additional operational time after the vac-bakes would contribute in any way to whisker growth?
During initial containment, the Torque Analyzers were not within their calibration date, however two analyzers were used to check each tool and if either had a suspect reading, the tool was sent to metrology. Additional Torque Analyzers are currently out for calibration and will be utilized during the forward containment plan | It is ironic (and very disappointing) that the torque analyzers themselves used in this initial evaluation were outside of their calibration date.
During initial containment, the Torque Analyzers were not within their calibration date, however two analyzers were used to check each tool and if either had a suspect reading, the tool was sent to metrology | Request the results from their recalibration to determine if these initial measured values used in the analysis are accurate or if all measurements need to be repeated.
Seeker Factory will check all torque tools with above mentioned torque analyzer, once per week for subassemblies (one assembly area per day) and once per day for Seeker level torques. The increased cadence on Seeker tools is due to low tact time in Seeker builds. | For the short term containment plan, what will be the action if a tool is found to be out of calibration during one of these checks?
Of those 24 tools, 13 have been used on flight hardware. The 13 Tools that touched flight hardware also failed the final Metrology final check | For the 13 tools that were used for flight hardware, request to provide the last date of calibration and the currently required calibration interval for each of these tools.
Of those 24 tools, 13 have been used on flight hardware | I assume these 24 tools have been calibrated many times before. Have any of these ever been found to be out of calibration? If so, what action was taken as a result?
As part of containment actions for a Gimbal Assembly Cable torque tool SOOT, additional torque tools were found out of tolerance but within their calibration dates, in use on the factory floor | The calibration interval for some of these tools was changed recently. Request for more information on when this occurred and the specific interval change that was made.
Torque analyzers were utilized in the Seeker factory to run a check of all torque tools on the floor. For conservatism, torque checks on the factory floor were to a 4% tolerance which is tighter than the tool and drawing tolerances. | So, I am assuming that of the tools shown as non-conforming the ones that measured within the engineering requirement are included in this notice since they were outside of the 4% tolerance used as part of the on-floor torque checks, correct?
All impacted joints utilize staking as a secondary locking method. | In the chart, there are several of the tools and associated applications that make no mention of staking being used. Is this consistent with the statement, “all impacted joints utilize staking as a secondary locking method”?
Supplier exciter isolator implemented a design and material change without notification. Exciter Isolator Bismuth Whisker Growth | What is the Exciter SN# and Supplier?
Exciter delivered from Supplier implemented a design and material change without notification | When was this Exciter delivered from Supplier?
Whisker growth is exacerbated with increased vacuum-bake cycles | How many Vacuum Bakes did this hardware see?
All exciter NCRs were reviewed and are unrelated to isolator performance. All exciters (installed in Seeker) were reviewed for non-conformances; 9 NCRs were written, but not related to this component or exciter output power | Was there any NCRs / failures on this exciter or Seeker related to the Bismuth Issue?
Defect seen at two different lots of the hardware. | Was this defect seen during FAI?
Defect seen at two different lots of the hardware. | What is the difference between these two lots?
Did qnotes scrub to look at qnotes history for this issue. | Is any hardware being replaced for this issue?
We performed manual microscopic inspections on WIP. Parts were inspected. | Are we saying some of the components are compliant
It is possible, but it would stop production. These parts are on tape and reel. Manual inspection prior to placement would require removing the parts from the tape, inspect, and repackage at an external vendor. LM is moving forward with only one LDC while the other LDC is at the supplier. Removing it from production to screen would stop production. The current process of inspecting after placement and touching up as necessary involves much less handling, meets the requirements, and keeps the parts moving in house | Still results in a non-compliant condition. Has LM investigated how long it would take for an outside house to inspect and repackage? Are parts from the LDC on one reel?
A solder joint fatigue analysis for the SIT thermal cycling environment for a reduced solder joint without fillets gives a predicted life. During SIT, the hardware is tested for 392 thermal cycles | Would like more information on how a reduced solder joint without fillets was analyzed for this fatigue analysis of SIT thermal cycling environment
Charts have been updated to show the inspectors misunderstanding of the requirement and additional training they received. | Are there other similar flat lug leads used in product that could also be subject to inspectors misunderstanding?
MACRO does not flow the 507-9-477 spec to Ultimate Linings as part of their purchase order, however they previously reviewed the spec with and received concurrence from Ultimate Linings that the material will meet all requirements of the spec. | Why doesn’t MACRO flow the 507-9-477 spec to Ultimate Linings as part of their purchase order? Shouldn’t they?
LTC have already issued a CAR (completed) to Ultimate Linings for more information | Can the completed LTC CAR to Ultimate Linings be provided for SHIELD review?
LTC CAR to Ultimate Linings is complete but Ultimate Linings reasoning for the viscosity change is currently unknown | If the LTC CAR to Ultimate Linings is complete, it’s unclear why the reasoning for the viscosity change is still unknown. Can we find out?
LM to generate a SCAR to LTC and MACRO upon QNote closure to capture Ultimate Lining’s root cause and any corrective actions noted at LTC, MACRO, and Ultimate Linings. | Has LM issued a SCAR to LTC and MACRO yet? If not, what’s the ECD to issue and receive responses?
Update to Heater Controller CCA required for use of FAB2 MOSFET. Heater Controller -41 configuration created. Heater Controller -21 CCA identified as having a FAB2 MOSFET | what is the required update include in order to convert a -21 CCA (with a FAB2 MOSFET installed) into a -41 CCA?
Identified -21 CCA in the COE to have their FAB2 MOSFET swapped for a FAB1 MOSFET and continued building as -21 CCA. Remaining -21 CCA in COE upgraded to -41 configuration | do we know if the -21 CCA found with a FAB2 MOSFET was a unit that was supposed to have had the MOSFET swapped with a FAB1 or was it a unit that was supposed to be upgraded in the COE to a -41 configuration?
The -21 CCA identified as having a FAB2 MOSFET but was supposed to have FAB1, and -41 CCA is supposed to have FAB2 | If this -21 CCA was found with a FAB2 MOSFET does this mean there is a -41 CCA somewhere with a FAB1 MOSFET?
10 FAB2 MOSFETs missing | How do you explain the 10 missing FAB2 MOSFETs? Could that imply that they were incorrectly installed?
We are currently performing PA level MOT test on known HC -21 containing FAB2 MOSFET. | Has a PA with a known HC -21 and FAB2 MOSFET ever passed the PA level MOD test?
The voltage regulation performance was captured for 25 samples. The plot shows voltage levels between certain percent out of specification | Is the voltage regulation performance consistent across all units or is there variation unit to unit that could potentially allow some units to pass and others to fail?
The results of Thales preliminary assessment can not be provided. | What is ECD for Thales assessment?
4 bad connector failures (J4 and J5) found in during production process | Of the 4 connector failures experienced during the production process, which ones were with J4 and which ones were with J5?
The failure was due to contact press-fit being pulled out from the socket. The connector had not been demated yet. | What would have caused this since the connector had only been mated, not demated yet?
discovery 3 was during post weld connector inspection where contact press-fit was pushed to the bottom of the socket. These connectors have not beend mated yet. | for discovery 3 where the contact press-fit was pushed to the bottom of the socket, what would have caused this to happen since these connectors have not yet been mated? Is there a proces that would explain this?
Some press-fit connector socket inserts or crowns were found missing. The issue was identified after test failure due to contact press-fit being pulled out from the socket | for the failures where the contact press-fit was pulled out from the socket, were the missing crowns located?
DPA results indicate that over-etching may have contributed to initial failure depicting a “worse” condition. | Awaiting PED qual DPA results
25 Missiles impacted for May | What affected date code parts are contained within the 25 affected May missiles?
No samples remain for 13686699-3 DC 1852 for Test | What is the hardware containment specifically for 13686699-3, DC 1852 with no available samples to test?
Final assessment: 13604083 were delivered fully compliant from Q-Tech | How is compliant test results for 13604083 relevant to the issue on these parts?
Shipped samples to the supplier for testing which once complete will bring all the following batches into compliance: LDCs 2225, 1852, 1842, 2225, 1852, 1842. | Are the LDCs stated all the affected LDCs for this issue ever used?
The supplier is now completing all testing for all LDCs where the data is missing | What is ECD for all testing to be completed for all affected LDCs?
All LDCs will have all testing performed | Request LM add action item in Missile IPT to report results of all testing for all affected LDCs.
Per SCD : “the testing shall be performed IAW the MIL standard”. What was NOT performed: Group A & B IAW Product Level B | Still unclear how this testing was missed when it is clearly called out on the SCD.
Three issues discovered with the PA&E Micro-D hermetic bulkhead connectors mated to the GPUR | How is this related to the previous PA&E connector risk assessment?
Chelmsford inspection of WIP showed 69 out of 132 IFPs contained defect i.e. 52%. Lufkin inspection of WIP showed 13 out of 15 IFPs contained defect i.e. 89% | Unclear how inspections in Lufkin and Chelmsford were able to determine some product was compliant. Please clarify.
LM will utilize RF Transformer LDC 2211 for new CCA production. LM has redlined all CCA to inspect for this condition and perform touch up mitigation operations | Given we can inspect for compliance, is it possible to screen LDC 2211 and utilize only conforming units in CCA build?
RF Transformer was found to be missing nickel plating. LM will rework all accessible nonconforming hardware. | Unclear how this condition can be reworked at LM if the nickel plating is missing.
PD2 is required for RX0 path, the primary path used to receive communications from the ground radar. PD1 is required for RX1 path | Is PD1 the X-band path?
Solder joint stress: the hardware sees maximum limit at launch shock (qual level). | The solder joint stress concern was evaluated using launch shock environment analysis and test (at qual level). Wouldn’t some evaluation of life be appropriate to assess solder joint life?
The non compliant hardware was introduced only for MRFDLR and not legacy MRFDL. | Assume that all MRFDLR development qual testing and SIT was performed with compliant parts. Is this correct?
Escape was generated as all hardware sold to date may contain this condition. SCAR will be issued to the supplier. | Escape investigation should work to identify root cause at the supplier and more accurately identify previous hardware affected
LM is planning to Rework connectors in stock. | how is LM planning to “rework” connectors in stock?
Complete Root Cause and Corrective Action investigation. Inspect sample from supplier before acceptance on future deliveries | until root cause is identified, unclear why only a sample of connectors from the supplier would be inspected on future deliveries. Recommend this be performed at 100%.
Engineering: Investigate ESS testing to see effects of vibration on solder flakes | as investigation into how ESS testing affects the solder flakes is still in-process. Therefore, SHIELD would need LM assurances for all affected missiles.
Containment: Total stock QTY 957 connectors | recommend entire quantity (QTY) of 957 be screened to determine if any compliant connectors are present and use those on near term production
SPN generated for 364 WIP IFP CCAs. No FOD observed at final assembly inspection. Connector DC2122. Sample size: 6. Final Inspection. 0 pints with flaky petals per connector. Connector DC2319. Sample size: TBD. IFP CCAs at final inspection showed no flaky petals and no FOD discovered. | this chart seems to suggest that 364 IFP CCAs have been inspected at final assembly with no FOD observed. However only 6 of DC2122 and 0 of DC2319 have actually been inspected. This is not sufficient evidence that FOD is not present in the population.
Escape generated to contain Qty 93 MSEs impacted by this constraint. QN for Qty 5 at Midsection Assembly level and Qty 23 at Missile Assembly level. MSE consists for RF assembly, MRFDLR, and missile assembly. | so the 93 at RF Assembly and MRFDLR level are contained on the escape but the 28 at midsection and missile level aren’t?
Flakiness is an ordinal classification that describes the Solder Petal’s tendency to detach from the gold surface of the connector pin. In this analysis, Flakiness has three classifications: Delicate – The majority of the Solder Petal’s mass was demonstrated to easily detach (Flake off) from the connector pin’s gold surface under minimal levels of contact force | Please better define “majority”, as related to the percentage of petals deemed “delicate”.
tested the effects that SMT reflow and inline cleaning have on the flakiness of the solder petals. . Installed connectors onto UDC PWBs. Sent the PWBs through Lufkin’s IFP reflow profile | how representative are the results of the SMT reflow/cleaning on connectors installed on UDC PWBs as compared to fully populated IFP CCAs?
Tiny flakes have been removed from connector in Chelmsford with sticky tool after Lufkin processing | are these tiny flakes seen on the entire population of connectors? How many have been verified to have these tiny flakes present?
Sticky tool removes tiny flakes from SnPb | Are we sure these flakes are tin-lead?
This creates an isolated pocket where FOD would be trapped. LM is planning to inspect pockets for FOD as part of continuing investigation | what is ECD for inspection of pockets for FOD?
Risk of FOD: FOD would be trapped inside. FOD observed could cause shorts if not removed | suggest MRFDLR with affected connectors be subjected to ESS and undergo post-test inspection to determine if FOD is truly captured within the identified pocket.
Largest FOD observed could cause shorts around U21 in CCA and would be detectable during production testing. No failures observed | while the largest size FOD could cause a production failure at U21 if located in the right position, there is no guarantee that production testing would always detect it. The FOD could shift locations after production test to a more susceptible position and could potentially cause failures in the field.
Corrective Action: Send parts back to supplier for evaluation, and issue SCAR | Why haven’t parts been sent back and SCAR issued to the supplier before now?
Based on evidence collected so far, the defect is likely supplier caused. Review other designs to see where Samtec connectors are used | Has LM engaged with Samtec about this issue? What are LM’s future plans to engage with them?
Based on evidence collected so far, the defect is likely supplier caused. Review other designs to see where Samtec connectors are used | What is the plan to get compliant connectors from them?
An incorrect inductor dash configuration was installed on the Interface CCA. The incorrect parts were packaged in a box. | Who packaged the parts incorrectly, Boeing or the inductor manufacturer?
Containment: All incorrect parts originated from lot number N00251534 | How do we know all incorrect parts are from lot number N00251534? How exactly was containment identified?
6 have been shipped on Seekers | Where are the 6 affected “shipped” Seekers located?
An incorrect inductor dash configuration was installed. All in house WIP reworked to print by Boeing | Were the affected WIP CCAs identified and reworked by Boeing inspected to ensure the inductors at all locations were the correct part?
The -37 part was packaged in a box that was labelled with the correct part number -47 | If the -37 parts were installed in the -47 part location, is it likely that the -47 parts were installed in -37 (or other dash number) locations? If so, what would that impact be?
Installing the -37 part at -47 location would not adversely affect the operation of the Interface CCA/Seeker | If the installation of the -37 parts in the -47 part location has no affect on the operation of the Interface CCA/Seeker, why exactly were different values of inductors selected as part of the design for these different locations?
The -37 part was packaged in a box that was labelled with the correct part number -47 | Does the usage of these -37 parts in the -47 locations decrease reliability or performance margins? If so, can that be quantified?
Even with wrong part, the system remains within acceptable operational limits | Would a temperature step type test (not a production test) or an E3 type test be useful in fully determining any detrimental impact with these incorrect parts?
Interface CCA is installed on the Power Assembly which is installed on the Seeker. 12 CCAs delivered to Seeker factory | Would there be any potential issue or risk of failure if these Interface CCAs were to get separated from the Seekers they were delivered in and installed in other Seekers during a future maintenance action?
Down-circuit components not affected by inductor-induced voltage drop. Component functional limits between 4.75V and 5.25V | Have all affected downstream components been verified to have operating specifications limits of 4.75V to 5.25V?
Noise bandwidth is improved. Even with wrong part, the system remains within acceptable operational limits | please explain the statement that the “noise bandwidth is improved” as a result of this incorrect part.
Voltage Drop Calculation: The voltage drop increased by 55mV by increasing the inductance. Ambient +5V power rail data pulled. Observed result indicates a total voltage drop of about 80 mV. 20mV delta between known good Power Assembly and known wrong part installed Power Assembly over temperature | the calculation shows a voltage drop increase of 55mV while the data at the +5V power rail shows around 80mV and the data on another slide also reflects a 20mV delta. Please clarify.
Ambient +5V power rail data pulled. Observed result indicates a total voltage drop. Voltage drop is consistent and stable during thermal cycling. Component functional limits between 4 75 V and 5.25 V | this is ambient data. How would this decrease over temperature? How close to the 4.75V could this get?
All in house WIP reworked to print | Why didn’t the operator catch the discrepancy for the incorrect parts that were actually installed? Does his/her work instruction require him/her to verify that the part number of the actual part being installed matches what is required by work instruction/engineering?
Incorrect parts have been allocated to multiple unique Wos. An incorrect inductor dash configuration was installed. | Does work instruction require inspector to verify that the part number of the actual part being installed matches what is required by work instruction/engineering?
Recommend Use As Is Low Risk | What are root cause and corrective action steps to be taken?
units inspected from the qual era did not display the nonconformance | what “nonconformance” did the 5 qual era units not exhibit?
LM Chelmsford will rework all accessible IFP WIP | is LM Chelmsford still reworking all accessible IFP WIP as stated?
a non-compliant component finish resulting in insufficient solder joints. Non-operating Qual Launch Shocks were performed to parts with solder fillet removed | The charts don’t reference the solder joint fatigue analysis and results performed for the SIT thermal cycling environment for a reduced solder joint without fillets
Preliminary risk assessement: Escape generated as all MRFDLRs sold to date may contain this condition. All IFP CCAs installed in LM WIP are contained on QN. All open nonconformances will be dispositioned "no defect" and closed accordingly | Would recommend an appendix to the original risk assessment be generated that discusses the change in interpretation from the preliminary risk assessment.
JYM5245 – CAM inventory under Quality hold | what’s the plan for affected Seeker JYM5245?
For the remaining WIP not identified as impacted, we spot checked about 20%. No additional issues were found during the 20% spot check | How many individual boards from WIP, not identified as impacted, were inspected as part of the 20% sample?
For non-serialized CCA components, there currently is no step or instruction to verify the part number marking on the component during installation. | unclear why an inspection can’t be included that verifies that the physical part marking (if available) matches what is required by work instruction/engineering
Identified -21 CCAs in WIP to have their FAB2 MOSFET swapped for a FAB1 MOSFET and continued building as -21 CCAs. 97 upgraded to -41 CCA | What is the required update include in order to convert a -21 CCA (with a FAB2 MOSFET installed) into a -41 CCA?
Identified -21 CCAs in COE WIP to have their FAB2 MOSFET swapped for a FAB1 MOSFET and continued building as -21 CCAs. 97 upgraded to -41 CCA | Do we know if the -21 CCA found with a FAB2 MOSFET was a unit that was supposed to have had the MOSFET swapped with a FAB1 or was it a unit that was supposed to be upgraded in the COE to a -41 configuration?
Identified -21 CCAs in COE WIP to have their FAB2 MOSFET swapped for a FAB1 MOSFET and continued building as -21 CCAs. 97 upgraded to -41 CCA | If this -21 CCA was found with a FAB2 MOSFET does this mean there is a -41 CCA somewhere with a FAB1 MOSFET?
Trace: 10 FAB2 MOSFETs missing | How does supplier explain the 10 missing FAB1 MOSFETs? Could that imply that they were incorrectly installed on -41 CCAs?
Identified -21 CCAs in COE WIP to have their FAB2 MOSFET swapped for a FAB1 MOSFET and continued building as -21 CCAs. 97 upgraded to -41 CCA | Is the operational impact for a FAB1 MOSFET on a -41 CCA the same as a FAB2 MOSFET on a -21 CCA? If not, please explain the difference
203 unique -21 CCAs identified as having a “FAB2” MOSFET. A Sample of 25 CCAs from WIP population of 96 selected at supplier and physically examined. | how the suspect population is only 25 Seekers?
97 -21 CCAs upgraded to -41 Configuration | Do we have objective evidence this was done on all of these? Are these also suspect?
10 FAB2 MOSFETs missing | What happened to them and the corresponding 10 missing hardware they were to be installed in?
37 in WIP and 25 used to Validate Traceability. A Sample of 25 CCAs from WIP population of 96 selected at supplier and physically examined | only 50 of the 203 are truly cleared?
1 Passed at PA MOD Testing, confirmed FAB 1 FET Present. Engineering currently performing testing on known HC -21 containing FAB2 FETs. | Has a PA with a known HC -21 and FAB2 MOSFET ever passed the PA level MOD test? Is this test performed at ambient only or over temperature?
Thales Preliminary Assessment (Due to the preliminary results Use-As-Is can not be provided). | What is ECD for Thales assessment? and
Test Effectiveness Analysis (Automated Tests Catches Issue at PA MOD Test due to High RMS Voltage) | What is ECD for completion of test effectiveness survey testing?
Identified 106 -21 CCAs in COE WIP to have their “FAB2” MOSFET swapped for a “FAB1” MOSFET | Why replace FAB2 MOSFETs with FAB1 MOSFETS on the 106 -21 CCAs found in COE. Can we clarify?
10 FAB2 MOSFETs missing. | Do we physically know what happened to the missing 10 FAB1 MOSFETs?
106 FAB1 MOSFETs located in inventory. 96 out of 106 CCAs had actual kits updated | 106 FAB1 MOSFETs located in inventory and only 96 CCAs had actual kits updated?
Engineering currently performing testing on known -21 containing FAB2 FETs. 8 Engineering HC have been assessed at different level of testing. PA Level MOD Test has Failed all 8 Units | Are there any additional -21 containing FAB2 FET units, above the 8 units tested, that could be tested at PA level to increase confidence that units in this configuration will always be screened out by the PA MOD test?
Metal-to-metal interfaces present potential risk during chemical immersion processes due to fluid/conversion coating entrapment in crevices and hardware which can lead to corrosion | Are there test methods available to assess the risk of developing corrosion over time? If so, have we considered performing a test?
LM recommends a deviation for UAI on flexes with delamination consistent with what has been observed in qual and production units | Relative to the proposed deviation; do we have an expectation as to when that will be drafted?
Work instructions to be updated to provide guidance as to which delamination conditions are covered under deviation | As for the work instructions providing guidance on conditions to be covered under the deviation; will that determination be made by an engineer, inspector or operator?
MRFDLR CCAs containing edge-mount GPO connectors have been found to have a solder splash within the GPO mating interface. Prior to discovering this condition, Lufkin has been performing rework as-needed to correct GPO center pin misalignment. | What operation, and where, introduced the solder splash inside these connectors? Is this a rework step? Why didn’t a post inspection step detect the issue?
This condition introduces risk for potential FOD to be generated during mate/de-mate cycle | For the mating/de-mating experiment, it doesn’t appear than an active ESS vibration test was performed after the assets were subjected to the multiple mate and de-mate actions. Wouldn’t this test be valuable in supporting the assessment that the FOD generated would not cause a short or other performance failure/degradation? Can a test like this be performed to gather that confidence?
Flakes have potential to become metallic FOD. No records of related FOD being found on parts | It’s a little unclear to me exactly where this FOD is located.
Inspection noticed solder flakes towards the base of the posts. Metallic FOD was visible at the base of the posts and within the plastic casing | Are these flakes located at the base of the posts between the posts and the plastic casing or on the surface of the posts (or both)?
Obtained X-Rays of mated connectors | Will need to see X-ray results of mated connectors before making a final assessment.
Connector FOD. Impact: MRFDLR W6 flex print. 100% of the connectors in house have been inspected | Would request LM perform visual inspection of connectors that have been exposed to MRFDLR ESS to see if the FOD remains in place or moves within the connector?
Containment: All production MRFDLRs have been built with the same lot. The connectors in house have been inspected | Was the MRFDLR qualified with this lot of connectors? Do we have access to that unit for possible inspection?
The 13717366 connector post length is 0.126”. The gold contact area of the connector with the socket is .100”. | Are the dimensions for post length and contact area shown at the worst case condition or nominal. If nominal, what is the worst case condition?
provide Seeker Quality the trace of CCAs washed in the Mega Ion Wash station since the 10/17 PM of the station Seeker will then trace to product in WIP and potentially delivered hardware suspected of this condition | the potential escape into Seekers is for CCAs processed after the PM on 10/17 and somehow did not get captured during normal inspection. Is this correct?
all WIP/Stock of wetbox CCAs only resulted in CCAs having trace amounts of conformal coat on the edge of the card. | what specific conformal coat residue was observed on the non-wetbox CCAs?
Dielectric Strength tests utilized a gap between electrodes of .003” and .1” | Why was a .003" gap also tested, does this correlate to the actual spacing within the PA? Is this more realistic?
1:1000 Uncured Humiseal to FC 72. 1:500 Uncured Humiseal to FC 72. 1:1000 ratio is conservative to what we have seen in the line stock checks at Boeing. | how the ratios used of uncured humiseal to FC-72 correlates to what was seen in the line stock checks. Can we estimate the amount of uncured humiseal present on the card edges and the volume of FC-72 in the PA and show a calculation of the ratio?
Dielectric Strength of Humiseal and FC 72 at .003". Performed additional testing at same gap for commonality to the spec sheet and a clear visual of what the spec limit is 38kV | he dielectric strength for the .003” case shows data below the 38kV limit. Unclear what risk this equates to.
Dielectric Strength at .1". J2: Flakes of Cured Humiseal. J4: Uncured Humiseal. J1 Dielectric Strength. J3 Dielectric Strength | The dielectric strength for the .1” case does not show data for the J2 (flakes of cured humiseal) or J4 (uncured humiseal) condition. Why?
A FC 72/Humiseal solution does not raise any corrosion or Seeker 30 year lifecycle concerns (Boeing M&P). | I would like to see M&P analysis of why this contamination does not have an aging impact on the Fluorinert.
LDC: 1517 Devices received at Jabil exceeded PMPCP greater than 5 year LDC restriction (~6 years). Loose inventory has been quarantined | successful fine/gross leak testing of a sample of LDC 1517 loose inventory is a prerequisite for their continued usage or if loose inventory will not be used and will be replaced with compliant hardware.
Gimbal Torque Tool SOOT Issue. This wrench was part of a “spare” set to be used when the “active” set was sent to calibration | Has Boeing completed a full analysis of all calibrated items, not just torque tools, to ensure that we do not have continued future escapes?
Corrective Action was the implementation of intermediate torque checks on the factory floor | are there additional corrective actions need to be implemented based on this discovery?
has submitted ten Material Review Requests (MRRs) for various dimensional nonconformances. Additional OOT (out of tolerance) Conditions | Do we understand what dimensions were out of tolerance and by how much?
As with the previous Delva nonconformances, our assessments indicate that all of the hardware conditions presented in the MRRs are low risk to delivered hardware | Clarify what exactly precipitated these additional findings that were not identified and resolved as part of the previous Delva escape?
The ten (10) impacted part numbers are as follows. 205 Discrepancies. 51 Additional OOT Conditions | 10 impacted part numbers (not 9) with a total of 205 discrepancies. However, only 51 are detailed in the follow-on slides. Please clarify.
91139-506 COVER, ADVANCED DIGITAL PROCESSOR REDESIGN. 1 Rejected/Accept Conforming Hardware only | For the 91139-506 ADPR (ADVANCED DIGITAL PROCESSOR REDESIGN) Cover, there is one discrepancy that is shown as “rejected/accept conforming hardware only”. Can LM/Boeing verify that no Seeker WIP or missiles awaiting sell-off contain this non-conforming condition?
Evaluate ‘new’ condition exhibited. Emulate and repeat investigation as found on previous 2023 Risk Assessment, including 30-year life testing – ECD 12/31 | Charts state that cross sections and life testing will be performed/completed by 12/31 for this “new condition”. Will any interim data be available prior to this?
At issue discovery, temporary stop works were put in place for QE containment inspection. This QE inspection was removed once the preforming process was implemented. No updates were made to permanently update the work instruction inspection operations to require inspection. | When was the previously incorporated QE inspection removed from the process (i.e. date)?
Work instructions were not detailed enough to prevent process drift associated with the sensitivity required when temporarily securing the flexes with tape. New operators lacked additional awareness and training. | Are the current process deficiencies operator dependent? That is, did any of the current operators perform the process as intended (or does nobody)?
At issue discovery, temporary stop works were put in place for QE containment inspection. No updates were made to permanently update the work instruction inspection operations to require inspection | Request LM provide additional information on the mechanism for adding temporary QA inspections/instructions (temporary stop works) and the mechanism/approval process for removal of these temporary actions.

## Accrynyms_for the training
Accronym | Meaning
MSE | Missile assembly
FOD | Foreign Object Debries
RCCA | Root Cause and Corrective Action
SHIELD | customer/government
LM | Lockheed
LDC | Lot date code
DC | Date code
IAW | In accordance with
Lufkin | LM
Chelmsford | LM
Camden | LM
Dallas | LM
Ocala | LM
SCAR | Supplier corrective action request
SnPb | tin-lead
ECD | Estimate completion date
TBD | To be determined
ESS | Energy storage system
CCA | Circuit card assembly
Samtec | supplier
Boeing | supplier
SCD | Source control drawing
PA&E | supplier
507-9-477 | LM specification
spec | specification
SN | serial number
PED | Plastic encapsulation device
GPUR | hardware
MRFDLR | hardware
CCA | hardware
WIP | Work in process
seeker | hardware
IFP | hardware
ESS | testing
MOFSET | hardware
PA | Power assembly
PA | hardware
WO | Work order
SIT | Solder Integrity Testing
SIT | Testing
MOSFET | hardware
CAM | Camden
Thales | subtier supplier